## Project Planner
EasyTeach
David Aflalo, Doron Azulay, Liron Farzam |  |  |  |  | Period Highlight: | 12 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Study Machine Learning | 8 | 6 | 8 | 6 | 40%
Study Python Environment | 1 | 4 | 1 | 4 | 90%
Define wanted Gestures | 4 | 2 | 4 | 2 | 100%
UI Mockup | 4 | 2 | 4 | 2 | 100%
Detailed System requirements | 4 | 3 | 4 | 3 | 100%
Design of gesture recognition engine | 6 | 3 | 6 | 3 | 100%
Implementation of Gesture Reconition Engine (GRE) | 9 | 8 | 9 | 8 | 40%
Tests of the GRE | 13 | 6 | 13 | 6 | 0%
Project Progress Presentation | 12 | 1 | 12 | 1 | 100%
Build the main application | 13 | 15 | 13 | 15 | 10%
Integration of GRE with application | 15 | 15 | 15 | 15 | 0%
Tests with users | 25 | 6 | 25 | 6 | 0%
Final project presentation (no audience) | 30 | 2 | 30 | 2 | 0%
Writing the report | 32 | 5 | 32 | 5 | 0%
Project Presentation (with audience) | 36 | 1 | 36 | 1 | 0%
Project report submission | 40 | 1 | 40 | 1 | 0%